## Project Tracker
Northlight Studio: Master Project Tracker
Every active initiative in one place. Status colors: On Track (green), At Risk (yellow), Blocked (red), Done (blue), Parked (grey). Reviewed in the Tuesday operating meeting; the Updates column is a running dated log.
SAMPLE. Northlight Studio is a fictional creative agency. Every name, date, figure, and entry in this workbook is invented for illustration.
Project | Area | Owner | Status | Next milestone | Target date | Dependencies | Notes | Updates
OPERATING CADENCE
Weekly operating rhythm | Ops | Founder + Studio director | On Track | Fourth consecutive week of all three meetings held | Sep 30 | Calendar holds; agenda template | Tue decisions, Wed build, Fri review. The three meetings are the system. | Sep 4 - all three held for the third week; decision meeting ran 35 min ¦ Aug 28 - build meeting skipped once; agreed no skipping
Two step creative review | Ops | Studio director | Done | Live | Done | Review criteria doc | Studio director approves standard work; founder sees new clients and flagged items only | Sep 4 - four weeks live; average turnaround down four days ¦ Aug 12 - criteria doc signed off
Founder two week absence test | Ops | Founder | On Track | Absence dates confirmed with clients | Nov 3 | Producer in seat; review workflow stable | The test the whole system was built to pass | Sep 4 - dates penciled for early Nov; client notice drafted
PRODUCER HIRE
Producer role | People | Studio director | On Track | Second round interviews | Sep 19 | Scorecard, question set, salary band | Removes the founder from day to day production scheduling | Sep 4 - three candidates through first round; two advancing ¦ Aug 25 - posting live
Onboarding plan | People | Studio director | Blocked | Draft 30 day plan | Sep 26 | Producer start date | Cannot finalize until the hire is made | Sep 4 - blocked on hire; outline started
FINANCE
Retainer price update | Finance | Founder | Done | Notices sent | Done | Client list, new rate card | New rate effective in 60 days; existing clients grandfathered through the window | Aug 20 - all eleven notices sent; two clients asked questions, none churned
Scope change protocol | Finance | Studio director | At Risk | First month of logged out of scope requests reviewed | Sep 12 | Request log, pricing sheet | Every out of scope request logged and either billed or waived in writing | Sep 4 - log exists but two requests went unlogged; reminder added to the Friday review
Subscription inventory | Finance | Bookkeeper | On Track | Four unused tools cancelled | Sep 30 | Card statements, owner per tool | Nineteen subscriptions found, four with no active user in 90 days | Sep 4 - two cancelled; two pending end of billing cycle ¦ Aug 15 - inventory complete
Accountant advisory session | Finance | Founder | Done | Held | Done | Question set | Margin by service line, estimated taxes, entity structure | Aug 28 - session held; margin by service line answered; follow up in Q4
MARKETING
Content calendar | Marketing | Marketing coordinator | On Track | Fall showcase campaign complete | Sep 30 | Client approvals, case study pages | Two posts per week minimum; founder writes one | Sep 4 - four posts published, three scheduled; see Content Calendar workbook
Kickoff checklist lead magnet | Marketing | Marketing coordinator | On Track | Landing page live | Sep 12 | Checklist PDF, email capture | First downloadable resource | Sep 4 - PDF final; page in build
Case study: skincare packaging | Marketing | Marketing coordinator | At Risk | Client sign off on photography | Sep 19 | Client approval | Third project in the Fall showcase | Sep 4 - client slow to respond; escalate via founder if no answer by Sep 10
PARKED
Website rebuild | Marketing | Founder | Parked | Revisit in Q1 | Q1 2027 | Producer hire; Q4 pipeline | Not a priority until the hire and the absence test are done | Aug 12 - parked by decision in the Tuesday meeting

## Decision Log
Northlight Studio: Decision Log
Every decision closed during the three week audit: when it was made, what state it was in before, what unblocked it, the data behind it, and what it unblocked next. Open recommendations live in the Project Tracker, not here.
SAMPLE. Northlight Studio is a fictional creative agency. Every name, date, figure, and entry in this workbook is invented for illustration.
Prior state: | Stalled = open weeks or months |  | Pre-discussed = raised, never landed |  | Surfaced in audit = new question
# | Decision | Date / week | Area | Prior state | What unblocked it | Data / inputs that fed it | What it unblocked next
1 | Engage for a three week Operating System Audit | Wk 0 | Engagement | Pre-discussed | Discovery call scoped the work | Founder overwhelm; two renewals due next quarter | The audit cadence and deliverables
2 | Set Tue/Wed/Fri operating rhythm; Mon/Thu protected for creative work | Wk 1 | Ops | Surfaced in audit | Kickoff session | Founder's stated energy map | All subsequent working sessions; client calls moved off Mon/Thu
3 | Renew the project management tool at a lower tier | Wk 1 | Software | Stalled | Usage data pulled per seat | Nineteen seats paid, eleven active | Annual saving; seat owner named
4 | Cancel the proofing tool; migrate three workflows | Wk 1 | Software | Stalled | Subscription inventory | No logins in 90 days; workflows rebuilt in the PM tool | Second renewal closed; inventory complete
5 | Retainer price update with 60 day notice and grandfathering | Wk 2 | Finance | Stalled | Margin by retainer calculated with unbilled revisions counted | Two proposals blocked on the unset rate | Two proposals sent; scope change protocol
6 | Adopt a two step creative review | Wk 2 | Ops | Pre-discussed | Review queue measured: average four day wait at founder | Delivery delays traced to founder review | Founder time freed; studio director authority formalized
7 | Write the scope change protocol | Wk 2 | Finance | Surfaced in audit | Retainer margin analysis | One unbilled revision round per retainer per month | Request log; Friday review item
8 | Assign owners on the Financial Responsibility Map | Wk 2 | Finance | Surfaced in audit | Obligation inventory built | Eleven recurring obligations, four unowned | Estimated taxes on the accountant's calendar
9 | Approve the producer scorecard and question set | Wk 3 | People | Stalled | Role scoped against the founder's time log | Founder spending 30% of time on production scheduling | Job posting; interview schedule
10 | Hold the accountant advisory session | Wk 3 | Finance | Pre-discussed | Question set written | Margin by service line unknown | First advisory conversation held
11 | Stand up the content calendar with a two post minimum | Wk 3 | Marketing | Surfaced in audit | Pillars and campaigns defined | Publishing had depended on founder spare time | Fall showcase campaign
12 | Park the website rebuild until Q1 | Wk 3 | Marketing | Pre-discussed | Tuesday decision meeting | Producer hire and absence test take priority | Q4 focus protected
13 | Schedule the founder absence test for early November | Wk 3 | Ops | Surfaced in audit | Roadmap review | Producer start date; review workflow stable | The 60 to 90 day test
14 | Set a 22 day review checkpoint with Ladyville | Wk 3 | Engagement | Surfaced in audit | Close out session | Roadmap handed over | Decision on ongoing support
| Decisions closed | 14
| Of which stalled | 4
| Of which pre-discussed | 4
| Of which surfaced in audit | 6

## Decision & Win Log
Northlight Studio x Ladyville: Decision & Win Log
Every decision, win, and lesson from the engagement, by date. Where the exact day was unclear, entries sit on that week's Friday as weekly wins.
SAMPLE. Northlight Studio is a fictional creative agency. Every name, date, figure, and entry in this workbook is invented for illustration.
Legend: | Decision | Win | Learning
Date | Day | Type | Entry | Area
Aug 3 | Mon | Decision | Discovery call: scoped a three week Operating System Audit; agreed pricing, cadence, and a 22 day review checkpoint | Engagement
Aug 10 | Mon | Decision | Kickoff: Tue/Wed/Fri operating rhythm set; founder's Mon/Thu protected for creative work | Cadence
Aug 12 | Wed | Decision | Project management tool renewed at a lower tier from seat usage data; proofing tool cancelled | Software
Aug 14 | Fri | Win | Subscription inventory complete: nineteen tools, four with no active user, two renewals now owned | Finance
Aug 14 | Fri | Learning | Reports were being generated and not read because no meeting existed to read them in. The Friday review now has a fixed slot for the flag list. | Finance
Aug 18 | Tue | Decision | Retainer rate updated; 60 day notice with grandfathering window | Finance
Aug 19 | Wed | Decision | Two step creative review adopted; studio director approves standard work | Ops
Aug 21 | Fri | Win | Two proposals that had waited on the unset rate went out the same week | Sales
Aug 21 | Fri | Learning | None of the stalled decisions lacked an answer. They lacked a container. The Tuesday meeting is the container. | Cadence
Aug 25 | Tue | Decision | Producer scorecard and question set approved; posting live | People
Aug 26 | Wed | Win | Financial Responsibility Map complete: eleven obligations, every one with an owner or explicitly marked unowned | Finance
Aug 28 | Fri | Win | First accountant advisory session held against the question set; margin by service line answered | Finance
Aug 28 | Fri | Decision | Website rebuild parked until Q1 | Marketing
Sep 1 | Tue | Decision | Founder absence test scheduled for early November | Ops
Sep 4 | Fri | Win | Third consecutive week with all three operating meetings held; review turnaround down four days | Cadence
Sep 4 | Fri | Decision | Close out: 30/60/90 roadmap handed over; 22 day checkpoint set | Engagement
Totals
|  |  | Decision | 9
|  |  | Win | 5
|  |  | Learning | 2